Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 13 July 2026 |
| --- | --- |
| Team ID | SWTID-2026-8055 |
| Project Name | Credit Card Approval Prediction System |
| Team Members | Thiruveedula Rohita Sri Venkata Siddardha |
| Maximum Marks | 5 Marks |

## Product Backlog & Sprint Schedule

| Sprint | Functional Requirement | Story No. | User Story / Task | Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Planning | USN-1 | Create project workflow and repository structure | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-1 | Project Planning | USN-2 | Collect GitHub repository and demo links | 1 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-1 | Data Collection | USN-3 | Generate synthetic dataset matching the Kaggle schema (generate_data.py) | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-1 | Data Analysis | USN-4 | Import libraries and read dataset | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-2 | Data Analysis | USN-5 | Perform univariate analysis | 2 | Medium | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-2 | Data Analysis | USN-6 | Perform multivariate analysis | 2 | Medium | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-2 | Data Analysis | USN-7 | Generate descriptive statistics | 1 | Medium | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-2 | Data Preprocessing | USN-8 | Handle missing values | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-3 | Data Preprocessing | USN-9 | Feature engineering (AGE_YEARS, YEARS_EMPLOYED) | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-3 | Data Preprocessing | USN-10 | Encode categorical variables and scale numeric features | 3 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-3 | Model Building | USN-11 | Build preprocessing + Random Forest pipeline | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-4 | Model Building | USN-12 | Train Random Forest classifier (class_weight=balanced) | 3 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-4 | Model Building | USN-13 | Evaluate model: accuracy, precision, recall, F1, ROC AUC | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-4 | Model Building | USN-14 | Export pipeline, metrics.json, and feature_meta.json | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-5 | Application Development | USN-15 | Develop HTML/CSS/JS user interface | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-5 | Application Development | USN-16 | Develop Flask backend (/, /api/meta, /api/predict, /api/submissions) | 3 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-5 | Application Development | USN-17 | Integrate trained model with Flask | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-5 | Testing & Deployment | USN-18 | Test application and fix bugs | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |
| Sprint-5 | Documentation | USN-19 | Prepare README, project report, and documentation | 2 | High | Thiruveedula Rohita Sri Venkata Siddardha |

## Project Tracker, Velocity & Burndown

| Sprint | Total Story Points | Duration | Start Date | End Date (Planned) | Points Completed | Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 9 | 6 Days | 07 Jul 2026 | 12 Jul 2026 | 9 | 12 Jul 2026 |
| Sprint-2 | 7 | 6 Days | 13 Jul 2026 | 18 Jul 2026 | 7 | 18 Jul 2026 |
| Sprint-3 | 7 | 6 Days | 20 Jul 2026 | 25 Jul 2026 | 7 | 25 Jul 2026 |
| Sprint-4 | 7 | 6 Days | 27 Jul 2026 | 01 Aug 2026 | 7 | 01 Aug 2026 |
| Sprint-5 | 9 | 6 Days | 03 Aug 2026 | 08 Aug 2026 | 9 | 08 Aug 2026 |

Velocity

Total story points = 39 across 5 sprints of 6 days each. Average velocity (AV) = 39 / 30 ≈ 1.3 story points per day.

Burndown Chart Data

| Sprint | Planned Story Points Remaining | Actual Story Points Remaining |
| --- | --- | --- |
| Start | 39 | 39 |
| Sprint 1 | 30 | 30 |
| Sprint 2 | 23 | 24 |
| Sprint 3 | 16 | 16 |
| Sprint 4 | 9 | 9 |
| Sprint 5 | 0 | 0 |